## Overview
OKR Implementation Timeline
A 6-month rollout template based on the Teamflect framework
How to use this template
1. | Open the 6-Month Timeline sheet. It contains all 23 implementation activities mapped across 26 weeks.
2. | Edit the Owner, Start Week, and End Week columns to match your team and schedule. The colored Gantt bars update automatically.
3. | Update the Status column as you progress. Status colors are applied automatically.
4. | Use the Notes column for context, blockers, or links to related docs.
5. | Open the Cycle Planner sheet to schedule your first four OKR cycles with team coverage.
Phase summary
Phase | Weeks | Focus
Phase 1 — Readiness | Weeks 1–3 | Confirm strategy, assign sponsor/coach/champion, choose pilot team.
Phase 2 — Launch | Weeks 4–6 | Run the first OKR workshop, document the set, schedule check-ins.
Phase 3 — Cycle 1 | Weeks 7–15 | Biweekly check-ins. Mid-cycle health check.
Phase 4 — Retro | Weeks 16–17 | Score OKRs, run start/stop/continue retrospective, plan cycle 2.
Phase 5 — Cycle 2 + Expand | Weeks 18–26+ | Onboard 2 more teams. Second workshop. Run cycle 2.
Status colors
Not Started
In Progress
Done
Blocked
Built by Teamflect. Pair this template with the full guide: How to Implement OKRs.

## 6-Month Timeline
[8 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | M7+
# | Activity | Phase | Owner | Start Wk | End Wk | Status | Notes | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 | Run readiness self-check (5-question) | Phase 1 | Sponsor | 1 | 1 | Not Started
2 | Validate strategy with leadership | Phase 1 | Sponsor | 1 | 2 | Not Started
3 | Choose pilot team | Phase 1 | Sponsor | 2 | 2 | Not Started
4 | Assign three OKR roles (sponsor, coach, champion) | Phase 1 | Sponsor | 2 | 3 | Not Started
5 | Lock OKR cadence company-wide | Phase 1 | Sponsor | 3 | 3 | Not Started
6 | Define implementation success (meta-objective) | Phase 1 | Coach | 3 | 3 | Not Started
7 | Schedule first OKR workshop | Phase 2 | Coach | 4 | 4 | Not Started
8 | Run first OKR workshop | Phase 2 | Coach | 5 | 5 | Not Started
9 | Document OKR set and assign KR owners | Phase 2 | Champion | 5 | 6 | Not Started
10 | Schedule biweekly check-ins | Phase 2 | Champion | 6 | 6 | Not Started
11 | Biweekly check-in 1 | Phase 3 | Champion | 8 | 8 | Not Started
12 | Biweekly check-in 2 | Phase 3 | Champion | 10 | 10 | Not Started
13 | Mid-cycle health check | Phase 3 | Coach | 11 | 12 | Not Started
14 | Biweekly check-in 3 | Phase 3 | Champion | 12 | 12 | Not Started
15 | Biweekly check-in 4 | Phase 3 | Champion | 14 | 14 | Not Started
16 | Final OKR scoring | Phase 4 | Champion | 16 | 16 | Not Started
17 | Cycle 1 retrospective (start/stop/continue) | Phase 4 | Coach | 17 | 17 | Not Started
18 | Plan cycle 2 — choose additional teams | Phase 4 | Sponsor | 17 | 17 | Not Started
19 | Onboard 2 additional pilot teams | Phase 5 | Coach | 18 | 19 | Not Started
20 | Run cycle 2 OKR workshops | Phase 5 | Coach | 19 | 20 | Not Started
21 | Document cycle 2 OKR sets | Phase 5 | Champions | 20 | 21 | Not Started
22 | Biweekly check-ins (all teams) | Phase 5 | Champions | 22 | 26 | Not Started
23 | Cycle 2 retrospective | Phase 5 | Coach | 26 | 26 | Not Started
Note on E2: Edit this number to shift the Gantt bar start. The bar will redraw automatically.
Note on F2: Edit this number to shift the Gantt bar end. The bar will redraw automatically.

## Cycle Planner
OKR Cycle Planner
Map the first four OKR cycles. Add teams as the rollout expands.
Cycle | Teams included | Workshop date | Retro date | Cycle length | Notes
Cycle 1 | 1 pilot team | [Set date] | [Set date] | 12 weeks (quarter) | Choose pilot per readiness criteria. Sponsor/coach/champion in place.
Cycle 2 | + 2 additional teams | [Set date] | [Set date] | 12 weeks | Same cadence as cycle 1. Apply retrospective learnings.
Cycle 3 | + Full department | [Set date] | [Set date] | 12 weeks | Cascade objectives. Coach internalised, less external support needed.
Cycle 4+ | Most of company | [Set date] | [Set date] | 12 weeks | Mature operating rhythm. Annual top-level OKRs aligned with quarterly team OKRs.
Biweekly check-in schedule
Every two weeks during the cycle. 5–10 minutes inside an existing team meeting.
Check-in # | Cycle 1 date | Cycle 2 date | Cycle 3 date | Cycle 4 date | Owner
Check-in 1 | [Set date] | [Set date] | [Set date] | [Set date] | Champion
Check-in 2 | [Set date] | [Set date] | [Set date] | [Set date] | Champion
Check-in 3 | [Set date] | [Set date] | [Set date] | [Set date] | Champion
Check-in 4 | [Set date] | [Set date] | [Set date] | [Set date] | Champion
Check-in 5 | [Set date] | [Set date] | [Set date] | [Set date] | Champion
Built by Teamflect. Edit blue cells. Status, dates, and team names should all be customized for your organization.