## Start Here
HR Onboarding Template
HR's checklist for paperwork, compliance and the first 90 days
How to use this workbook
This template covers HR's side of onboarding, from the signed offer to the probation review. Use it alongside the hiring manager's plan so nothing falls between HR and the hiring team.
Enter the new hire's details on this sheet. The start date drives every due date in the Checklist tab.
Light purple cells are for you to edit. White cells hold formulas or guidance, so leave those as they are.
Pick a status for each task, document and policy as you go. The Progress tab updates on its own.
Add rows for company-specific tasks by copying an existing row so the formulas come with it. Keep sensitive documents in your HRIS rather than in this workbook.
New hire details
Field | Value
Employee name
Employee ID
Job title
Department
Hiring manager
HR owner
Employment type (full-time / part-time / contract)
Start date | 2026-12-07
Work location
Probation end date | 2027-03-07
Example start date shown. Replace it with the real one. Probation end defaults to 90 days after the start date.
Run HR onboarding inside Microsoft Teams
Teamflect keeps onboarding tasks, surveys, 1:1s and probation reviews in one place inside Microsoft Teams. See how it works at teamflect.com.

## Checklist
Onboarding checklist
Due dates calculate from the start date on the Start Here tab. Edit owners, offsets and statuses in the light purple cells.
Phase | Task | Owner | Days from start | Due date | Status | Notes | Overdue?
Offer and contract | Send the offer letter and track acceptance | HR | -21 | 2026-11-16 | Not started
Offer and contract | Issue the employment contract for signature | HR | -18 | 2026-11-19 | Not started
Offer and contract | Run background or reference checks, if you use them | HR | -18 | 2026-11-19 | Not started
Offer and contract | Create the employee record in your HRIS | HR | -14 | 2026-11-23 | Not started
Offer and contract | Confirm start date, pay and reporting line | HR | -14 | 2026-11-23 | Not started
Preboarding paperwork | Send the new hire paperwork pack | HR | -14 | 2026-11-23 | Not started
Preboarding paperwork | Verify identity and right-to-work documents | HR | -7 | 2026-11-30 | Not started
Preboarding paperwork | Collect tax forms and bank details for payroll | Payroll | -7 | 2026-11-30 | Not started
Preboarding paperwork | Collect emergency contact details | HR | -7 | 2026-11-30 | Not started
Preboarding paperwork | Send the employee handbook for review | HR | -7 | 2026-11-30 | Not started
Preboarding paperwork | Share benefits options and enrollment deadlines | HR | -5 | 2026-12-02 | Not started
Systems and setup | Request accounts and equipment from IT | HR | -10 | 2026-11-27 | Not started
Systems and setup | Add the new hire to payroll | Payroll | -5 | 2026-12-02 | Not started
Systems and setup | Add the new hire to the org chart and directory | HR | -3 | 2026-12-04 | Not started
Systems and setup | Set up the new hire in your performance tool | HR | -3 | 2026-12-04 | Not started
Systems and setup | Check the manager has a 30-60-90 day plan ready | HR | -3 | 2026-12-04 | Not started
Systems and setup | Send the welcome email with day one logistics | HR | -3 | 2026-12-04 | Not started
Day one | HR welcome and orientation session | HR | 0 | 2026-12-07 | Not started
Day one | Collect any outstanding signed documents | HR | 0 | 2026-12-07 | Not started
Day one | Walk through benefits, leave and pay dates | HR | 0 | 2026-12-07 | Not started
Day one | Confirm the new hire can sign in to the HR system | IT | 0 | 2026-12-07 | Not started
Day one | Explain how to raise questions or concerns with HR | HR | 0 | 2026-12-07 | Not started
First 30 days | Send the week one onboarding survey | HR | 7 | 2026-12-14 | Not started
First 30 days | Complete mandatory compliance training | New hire | 14 | 2026-12-21 | Not started
First 30 days | Collect signed policy acknowledgments | HR | 14 | 2026-12-21 | Not started
First 30 days | Confirm benefits enrollment is complete | HR | 30 | 2027-01-06 | Not started
First 30 days | Check the first payroll run is correct | Payroll | 30 | 2027-01-06 | Not started
First 30 days | 30-day HR check-in with the new hire | HR | 30 | 2027-01-06 | Not started
Days 31 to 90 | Send the 30-day onboarding survey | HR | 31 | 2027-01-07 | Not started
Days 31 to 90 | Remind the manager about the 60-day goal review | HR | 56 | 2027-02-01 | Not started
Days 31 to 90 | Schedule the probation review meeting | HR | 74 | 2027-02-19 | Not started
Days 31 to 90 | Hold the probation review meeting | Manager | 88 | 2027-03-05 | Not started
Days 31 to 90 | Record the probation outcome in your HRIS | HR | 88 | 2027-03-05 | Not started
Days 31 to 90 | Send the 90-day onboarding survey | HR | 88 | 2027-03-05 | Not started
Formulas:
Due date = IF([Days from start]="","",'Start Here'!$B20+[Days from start])
Overdue? = IF(AND([Due date]<>"",[Due date]<TODAY(),[Status]<>"Done",[Status]<>"N/A"),"Overdue","")

## Progress
Onboarding progress
This tab updates automatically from the Checklist. Tasks marked N/A don't count toward the total.
Phase | Tasks | Done | % complete | Overdue
Offer and contract | 5 | 0 | 0% | 0
Preboarding paperwork | 6 | 0 | 0% | 0
Systems and setup | 6 | 0 | 0% | 0
Day one | 5 | 0 | 0% | 0
First 30 days | 6 | 0 | 0% | 0
Days 31 to 90 | 6 | 0 | 0% | 0
Total | 34 | 0 | 0% | 0
Owner | Open tasks | Done
HR | 28 | 0
Payroll | 3 | 0
IT | 1 | 0
Manager | 1 | 0
New hire | 1 | 0
Compliance | Total | Complete | % complete
Documents verified | 12 | 0 | 0%
Policies signed | 8 | 0 | 0%

## Documents
Document tracker
Track each document from request to verification. Store the documents themselves in your HRIS, not in this file.
Document | Required? | Status | Date received | Verified by | Notes
Signed offer letter | Yes | Pending
Signed employment contract | Yes | Pending
Proof of identity | Yes | Pending
Right-to-work documents | Yes | Pending
Tax forms | Yes | Pending
Bank details for payroll | Yes | Pending
Emergency contact form | Yes | Pending
Confidentiality agreement or NDA | Yes | Pending
Background check result (if applicable) | Yes | Pending
Benefits enrollment forms | Yes | Pending
Equipment agreement | Yes | Pending
Handbook acknowledgment | Yes | Pending

## Policies
Policy acknowledgments
Record when each policy was shared and when the employee signed it.
Policy | Shared on | Signed on | Status | Notes
Employee handbook |  |  | Not shared
Code of conduct |  |  | Not shared
Anti-harassment policy |  |  | Not shared
Data privacy and security policy |  |  | Not shared
IT acceptable use policy |  |  | Not shared
Health and safety policy |  |  | Not shared
Remote or hybrid work policy |  |  | Not shared
Leave and time-off policy |  |  | Not shared

## Surveys
Onboarding surveys
Suggested questions: How clear was the information you got before day one? Did you have the equipment and access you needed on day one? How well do you understand what's expected of you in your role? How likely are you to recommend working here to a friend? (0 to 10)
Survey | Send on | Sent | Responded | Score (0 to 10) | Key feedback | Action taken
Week one | 2026-12-14
Day 30 | 2027-01-07
Day 90 | 2027-03-05
Average score

## Probation
Probation review
Complete at the end of the probation period and file a signed copy in the employee record.
Item | Value
Probation end date | 2027-03-07
Review date
Outcome
If extended, new end date
Summary of performance
Agreed next steps
Sign-off | Name | Signature | Date
Employee
Manager
HR