## Start Here
New Hire Onboarding Template
A 90-day plan for managers, HR, IT and the new hire
How to use this workbook
This template gives everyone involved in onboarding one shared plan for a new hire's first 90 days. Fill in the new hire's details, check the owner and due date for each task, and tick items off as you go.
Enter the new hire's details on this sheet. The start date drives every due date in the Checklist tab.
Light purple cells are for you to edit. White cells hold formulas or guidance, so leave those as they are.
In the Checklist tab, pick a status for each task. The Progress tab updates on its own.
Add rows for company-specific tasks by copying an existing row so the formulas come with it.
New hire details
Field | Value
New hire name
Job title
Department
Manager
Onboarding buddy
HR contact
Start date | 2026-11-02
Work location (office / remote / hybrid)
Work email
Probation end date | 2027-01-31
Example start date shown. Replace it with the real one. Probation end defaults to 90 days after the start date.
Run this plan inside Microsoft Teams
Teamflect lets you assign onboarding tasks, schedule recurring 1:1s and track 30-60-90 day goals without leaving Microsoft Teams. See how it works at teamflect.com.

## Checklist
Onboarding checklist
Due dates calculate from the start date on the Start Here tab. Edit owners, offsets and statuses in the light purple cells.
Phase | Task | Owner | Days from start | Due date | Status | Notes | Overdue?
Before day one | Send the signed offer letter and confirm the start date | HR | -14 | 2026-10-19 | Not started |  | Overdue
Before day one | Collect tax, payroll and right-to-work paperwork | HR | -10 | 2026-10-23 | Not started
Before day one | Order the laptop, monitor and accessories | IT | -10 | 2026-10-23 | Not started
Before day one | Assign an onboarding buddy | Manager | -7 | 2026-10-26 | Not started
Before day one | Create email, Microsoft 365 and Teams accounts | IT | -5 | 2026-10-28 | Not started
Before day one | Draft the new hire's 30-60-90 day plan | Manager | -5 | 2026-10-28 | Not started
Before day one | Grant access to the tools the role needs | IT | -3 | 2026-10-30 | Not started
Before day one | Prepare the desk or ship equipment to remote hires | IT | -3 | 2026-10-30 | Not started
Before day one | Book first-week meetings in the new hire's calendar | Manager | -3 | 2026-10-30 | Not started
Before day one | Send a welcome email with day one logistics | Manager | -3 | 2026-10-30 | Not started
Before day one | Tell the team who's joining and when | Manager | -4 | 2026-10-29 | Not started
Day one | Welcome meeting with the manager | Manager | 0 | 2026-11-02 | Not started
Day one | Set up the laptop and sign in to every account | IT | 0 | 2026-11-02 | Not started
Day one | Office tour or virtual team introduction | Buddy | 0 | 2026-11-02 | Not started
Day one | Lunch or virtual coffee with the team | Buddy | 0 | 2026-11-02 | Not started
Day one | Walk through the first week schedule | Manager | 0 | 2026-11-02 | Not started
Day one | Read the employee handbook and key policies | New hire | 0 | 2026-11-02 | Not started
Day one | End-of-day check-in for questions | Manager | 0 | 2026-11-02 | Not started
First week | Review team goals and how the role contributes to them | Manager | 2 | 2026-11-04 | Not started
First week | Shadow a teammate on a live project | Buddy | 3 | 2026-11-05 | Not started
First week | Complete required compliance training | New hire | 4 | 2026-11-06 | Not started
First week | Meet each team member for a short 1:1 | New hire | 4 | 2026-11-06 | Not started
First week | Agree on 30-60-90 day goals | Manager | 4 | 2026-11-06 | Not started
First week | First weekly 1:1 with the manager | Manager | 4 | 2026-11-06 | Not started
First week | Send the week one feedback survey | HR | 4 | 2026-11-06 | Not started
Days 8 to 30 | Complete role-specific training | New hire | 21 | 2026-11-23 | Not started
Days 8 to 30 | Meet key stakeholders outside the team | New hire | 21 | 2026-11-23 | Not started
Days 8 to 30 | Confirm benefits enrollment | HR | 30 | 2026-12-02 | Not started
Days 8 to 30 | Deliver a first small project or quick win | New hire | 30 | 2026-12-02 | Not started
Days 8 to 30 | 30-day check-in and feedback conversation | Manager | 30 | 2026-12-02 | Not started
Days 31 to 60 | Share feedback on the onboarding experience so far | New hire | 45 | 2026-12-17 | Not started
Days 31 to 60 | Take ownership of recurring responsibilities | New hire | 60 | 2027-01-01 | Not started
Days 31 to 60 | 60-day check-in and goal review | Manager | 60 | 2027-01-01 | Not started
Days 61 to 90 | Work independently on core responsibilities | New hire | 90 | 2027-01-31 | Not started
Days 61 to 90 | Set goals for the next quarter | Manager | 90 | 2027-01-31 | Not started
Days 61 to 90 | 90-day review and probation decision | Manager | 90 | 2027-01-31 | Not started
Days 61 to 90 | Send the final onboarding survey | HR | 90 | 2027-01-31 | Not started
Formulas:
Due date = IF([Days from start]="","",'Start Here'!$B19+[Days from start])
Overdue? = IF(AND([Due date]<>"",[Due date]<TODAY(),[Status]<>"Done",[Status]<>"N/A"),"Overdue","")

## Progress
Onboarding progress
This tab updates automatically from the Checklist. Tasks marked N/A don't count toward the total.
Phase | Tasks | Done | % complete | Overdue
Before day one | 11 | 0 | 0% | 1
Day one | 7 | 0 | 0% | 0
First week | 7 | 0 | 0% | 0
Days 8 to 30 | 5 | 0 | 0% | 0
Days 31 to 60 | 3 | 0 | 0% | 0
Days 61 to 90 | 4 | 0 | 0% | 0
Total | 37 | 0 | 0% | 1
Owner | Open tasks | Done
HR | 5 | 0
Manager | 15 | 0
IT | 5 | 0
Buddy | 3 | 0
New hire | 9 | 0

## 30-60-90 Plan
30-60-90 day plan
Agree on these goals together during week one. Revisit them at each check-in.
Phase | Focus | What this looks like | Goals | How we'll measure success
First 30 days | Learn | Understand the team, the product, customers and how work gets done.
Days 31 to 60 | Contribute | Take on real work with support and start owning smaller pieces.
Days 61 to 90 | Own | Run core responsibilities independently and set goals for what's next.

## Check-ins
Check-in log
Questions to cover: What's been easier or harder than you expected? Do you have the access, tools and information you need? Which goals are on track, and where do you need support? What's one thing we could improve about onboarding?
Check-in | Target date | Date held | What's going well | Where support is needed | Agreed next steps
End of week one | 2026-11-07
End of week two | 2026-11-14
Day 30 | 2026-12-02
Day 60 | 2027-01-01
Day 90 | 2027-01-31

## Key Contacts
People to meet
Fill in names during preboarding so the new hire knows who to ask from day one.
Role | Name | Email or Teams handle | Why talk to them | Met?
Manager |  |  | Goals, priorities and weekly 1:1s
Onboarding buddy |  |  | Day-to-day questions and unwritten rules
HR contact |  |  | Payroll, benefits and policies
IT support |  |  | Accounts, access and equipment
Skip-level manager |  |  | Wider context on the team's goals