## Hiring Timeline
HIRING TIMELINE TEMPLATE
Plan every stage of a req from approval to day one. Edit the blue cells only.
| Role being hired | Customer Success Manager |  |  | Blue text = your inputs. Black = calculated, don't overwrite.
| Hiring manager | Dana Whitfield |  |  | Target start date: | 2026-11-12
| Kick-off date | 2026-09-07 |  |  | Total time to hire: | 67 calendar days
TIMELINE (week commencing)
# | Stage | Owner | Starts day | Days | Start date | End date | Status | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09
1 | Role approval & intake | Hiring Manager | 0 | 3 | 2026-09-07 | 2026-09-09 | Not started
2 | Job description & posting | Recruiter | 3 | 2 | 2026-09-10 | 2026-09-11 | Not started
3 | Sourcing & applications | Recruiter | 5 | 14 | 2026-09-12 | 2026-09-25 | Not started
4 | Resume screening | Recruiter | 10 | 10 | 2026-09-17 | 2026-09-26 | Not started
5 | Phone screens | Recruiter | 14 | 7 | 2026-09-21 | 2026-09-27 | Not started
6 | Hiring manager interviews | Hiring Manager | 21 | 7 | 2026-09-28 | 2026-10-04 | Not started
7 | Skills assessment / work sample | Hiring Manager | 28 | 5 | 2026-10-05 | 2026-10-09 | Not started
8 | Panel interviews | Interview Panel | 33 | 7 | 2026-10-10 | 2026-10-16 | Not started
9 | Final interview & debrief | Department Head | 40 | 4 | 2026-10-17 | 2026-10-20 | Not started
10 | Reference & background checks | HR Operations | 44 | 5 | 2026-10-21 | 2026-10-25 | Not started
11 | Offer & negotiation | Recruiter | 49 | 4 | 2026-10-26 | 2026-10-29 | Not started
12 | Offer accepted to day one | HR Operations | 53 | 14 | 2026-10-30 | 2026-11-12 | Not started
How to use: set your kick-off date in C6, then adjust 'Starts day' (days after kick-off) and 'Days' for each stage. Bars redraw automatically.
Stage durations shown are illustrative defaults for a mid-level individual contributor role. Replace them with your own historical time-to-hire data.
Template by Teamflect ¦ teamflect.com