## Onboarding Timeline
EMPLOYEE ONBOARDING TIMELINE TEMPLATE
Pre-boarding through the 90-day review, mapped across five phases.
| New hire name | Priya Raman |  |  | Start date and End date calculate automatically. Every other column is yours to edit.
| Role & manager | Customer Success Manager / Dana Whitfield |  |  | 'Day' is counted from the first day at work. Negative numbers are pre-boarding.
| First day at work | 2026-09-21 |  |  | 90-day onboarding complete: Tue, 22 Dec 2026
TIMELINE (week commencing)
# | Onboarding activity | Owner | Day | Days | Start date | End date | Status | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
BEFORE DAY ONE · PRE-BOARDING
1 | Offer accepted & contract signed | HR Operations | -14 | 2 | 2026-09-07 | 2026-09-08 | Not started
2 | Equipment ordered & accounts created | IT | -10 | 6 | 2026-09-11 | 2026-09-16 | Not started
3 | Welcome email & first-week agenda sent | Hiring Manager | -5 | 1 | 2026-09-16 | 2026-09-16 | Not started
4 | Buddy or mentor assigned | Hiring Manager | -5 | 2 | 2026-09-16 | 2026-09-17 | Not started
5 | Workspace & team announcement ready | HR Operations | -2 | 2 | 2026-09-19 | 2026-09-20 | Not started
DAY ONE & WEEK ONE · ORIENTATION
6 | Day one welcome & team introductions | Hiring Manager | 0 | 1 | 2026-09-21 | 2026-09-21 | Not started
7 | Systems, tools & access walkthrough | IT | 0 | 2 | 2026-09-21 | 2026-09-22 | Not started
8 | Compliance & policy training | HR Operations | 2 | 3 | 2026-09-23 | 2026-09-25 | Not started
9 | Role expectations & 90-day goals set | Hiring Manager | 2 | 3 | 2026-09-23 | 2026-09-25 | Not started
10 | First 1-on-1 with manager | Hiring Manager | 4 | 1 | 2026-09-25 | 2026-09-25 | Not started
DAYS 1-30 · LEARNING
11 | Stakeholder introduction meetings | Buddy | 7 | 10 | 2026-09-28 | 2026-10-07 | Not started
12 | Role & product training modules | Enablement | 7 | 16 | 2026-09-28 | 2026-10-13 | Not started
13 | Shadowing & first owned task | Buddy | 14 | 12 | 2026-10-05 | 2026-10-16 | Not started
14 | Onboarding experience survey | HR Operations | 21 | 1 | 2026-10-12 | 2026-10-12 | Not started
15 | 30-day check-in review | Hiring Manager | 30 | 1 | 2026-10-21 | 2026-10-21 | Not started
DAYS 31-60 · CONTRIBUTING
16 | First independently owned project | Hiring Manager | 31 | 26 | 2026-10-22 | 2026-11-16 | Not started
17 | Peer feedback collected | Buddy | 40 | 5 | 2026-10-31 | 2026-11-04 | Not started
18 | Mid-point coaching 1-on-1 | Hiring Manager | 45 | 1 | 2026-11-05 | 2026-11-05 | Not started
19 | 60-day check-in review | Hiring Manager | 60 | 1 | 2026-11-20 | 2026-11-20 | Not started
DAYS 61-90 · OWNING THE ROLE
20 | Full workload handover | Hiring Manager | 61 | 21 | 2026-11-21 | 2026-12-11 | Not started
21 | Progress review against 90-day goals | Hiring Manager | 75 | 3 | 2026-12-05 | 2026-12-07 | Not started
22 | 90-day review & probation decision | Hiring Manager | 90 | 1 | 2026-12-20 | 2026-12-20 | Not started
23 | Move to standard review cycle | HR Operations | 90 | 3 | 2026-12-20 | 2026-12-22 | Not started
How to use: set the first day at work in C6. Every date recalculates from it, and the timeline bars redraw automatically.
Activities and durations are illustrative defaults for a mid-level individual contributor role. Adjust them to your own onboarding programme.
Template by Teamflect ¦ teamflect.com