## Campaign Timeline
SALES & MARKETING TIMELINE TEMPLATE
One shared campaign schedule for both teams, from planning through to the retro.
| Campaign name |  | Q4 Microsoft Teams Bundle Push |  |  | Start date and End date calculate automatically. Every other column is yours to edit.
| Campaign owner |  | Demand Gen Lead / Sales Lead |  |  | 'Day' is counted from launch day. Negative numbers are pre-launch build work.
| Launch date |  | 2026-10-12 |  |  | Campaign wraps: Mon, 23 Nov 2026
| Bar colour by owning team: | [5 empty] | Marketing |  |  | Sales |  |  | Both teams
TIMELINE (week commencing)
# | Campaign activity | Team | Owner | Day | Days | Start date | End date | Status | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30
PRE-LAUNCH · PLANNING
1 | Campaign goals & target segments agreed | Both | Demand Gen + Sales Lead | -42 | 5 | 2026-08-31 | 2026-09-04 | Not started
2 | Offer, pricing & core messaging locked | Marketing | Product Marketing | -37 | 5 | 2026-09-05 | 2026-09-09 | Not started
3 | Target account list built & scored | Sales | Sales Ops | -35 | 7 | 2026-09-07 | 2026-09-13 | Not started
4 | Channel plan & budget approved | Marketing | Demand Gen | -30 | 4 | 2026-09-12 | 2026-09-15 | Not started
PRE-LAUNCH · BUILD
5 | Creative & landing page production | Marketing | Content + Design | -25 | 12 | 2026-09-17 | 2026-09-28 | Not started
6 | Email sequences & nurture flows built | Marketing | Marketing Ops | -18 | 10 | 2026-09-24 | 2026-10-03 | Not started
7 | Sales collateral & battlecards ready | Marketing | Product Marketing | -14 | 7 | 2026-09-28 | 2026-10-04 | Not started
8 | Sales briefing & enablement session | Sales | Sales Enablement | -7 | 2 | 2026-10-05 | 2026-10-06 | Not started
9 | CRM tracking, UTMs & lead routing tested | Marketing | Marketing Ops | -5 | 3 | 2026-10-07 | 2026-10-09 | Not started
LAUNCH WEEK
10 | Campaign goes live | Marketing | Demand Gen | 0 | 1 | 2026-10-12 | 2026-10-12 | Not started
11 | Paid & social amplification | Marketing | Demand Gen | 0 | 7 | 2026-10-12 | 2026-10-18 | Not started
12 | Launch email send | Marketing | Marketing Ops | 1 | 1 | 2026-10-13 | 2026-10-13 | Not started
13 | Outbound sequences begin | Sales | SDR Team | 1 | 6 | 2026-10-13 | 2026-10-18 | Not started
FOLLOW-UP · DAYS 7-30
14 | Inbound lead qualification & routing | Sales | SDR Team | 7 | 21 | 2026-10-19 | 2026-11-08 | Not started
15 | Follow-up calls & demos booked | Sales | Account Executives | 7 | 21 | 2026-10-19 | 2026-11-08 | Not started
16 | Retargeting & second email wave | Marketing | Demand Gen | 10 | 14 | 2026-10-22 | 2026-11-04 | Not started
17 | Weekly pipeline review | Both | Demand Gen + Sales Lead | 14 | 1 | 2026-10-26 | 2026-10-26 | Not started
WRAP-UP · DAYS 30-45
18 | Campaign performance reporting | Marketing | Marketing Ops | 30 | 5 | 2026-11-11 | 2026-11-15 | Not started
19 | Closed-won attribution review | Sales | Sales Ops | 33 | 3 | 2026-11-14 | 2026-11-16 | Not started
20 | Retro & learnings documented | Both | Demand Gen + Sales Lead | 40 | 3 | 2026-11-21 | 2026-11-23 | Not started
How to use: set the launch date in D6. Everything before and after it recalculates, and the bars recolour by whichever team owns the activity.
Activities and durations are illustrative defaults for a mid-sized B2B campaign. Adjust them to your own channel mix and sales cycle.
Template by Teamflect ¦ teamflect.com